## TODO
Categorie | Type | Tache | Estimation | Temps Passé | Reste à Faire | Avancement
DOCKER |  | Environnement docker | 15 | 5 | 0% | 100%
Connexion | Database | TABLE : users → roles → permission → permission | 10 | 0
Connexion | Metier | Model : User extends Authenticatable | 5 | 0
Connexion | Controller | Controller : LoginController use AuthenticatesUsers | 3 | 0
Connexion | View | View : auth/login.blade (email,password) | 5 | 0
DASHBOARD | Database | TABLE: task → lead → project → client → Setting
DASHBOARD | Metier | Model : fonction:count() → task → lead → project → client → Setting -->fonction:get()
DASHBOARD | Controller | Controller : PagesController : fonction : dashboard() return {datasheettotal,user,absences,totalTasks,totalLeads,totalProjects,totalClients,} → url(‘/dashboard’)
DASHBOARD | View | View : pages/dashboard →totalTasks,totalLeads,totalProjects,totalClients
DASHBOARD | View | View : pages/_createdGraph →chart (datasheet)
DASHBOARD | View | View : pages/_users →Online User
DASHBOARD | View | View : pages/_absent →Absent User Today
DASHBOARD | View | View : Integration : pages/createdGraph → _users → _absent with page/dashboard
CLIENTS | Database | TABLE : contact → clients
CLIENTS | Metier | Model : Contact → clients : (fonction → insertion → findAll → delete → show)
SALES → Products | * | *
SALES → Overdue

## Sheet2
Days |  | Categorie | Type | Tache | Estimation | Temps Passé | Reste à Faire | Avancement
Jour1 | ExistingApp | DOCKER | ENVIRONNEMENT | Environnement docker | 15 | 5 | 0% | 100%
Jour1 | ExistingApp | MCD | MCD | Creation du MCD | 120 | 20 | 0% | 100%
Jour1 | ExistingApp | RENITALISATION | METIER | Service : TableResetter - resetTable(array table) | 16 | 2 | 0% | 100%
Jour1 | ExistingApp | RENITALISATION | CONTROLLER | DatabaseResetController - resetSpecificTables() -> url(reset-tables) | 10 | 5 | 0% | 100%
Jour1 | ExistingApp | TESTEUR | TESTEUR | TEST DES UNE PAR UNE SIDEBAR | 100 | 30 | 80% | 20%
Jour1 | ExistingApp | RESOLUTION ERROR | RESOLUTION ERROR | RESOLUTION ERROR | 30 | 30 | 80% | 20%
Jour2 | ExistingApp | IMPORT TEST | METIER | ImportExportService - handleFileErrors(), adjustColumnMappings(), readCSVFile(), prepareTables(), import() | 20 | 2 | 0% | 100%
Jour2 | ExistingApp | IMPORT TEST | CONTROLLER | ImportController - showImportForm(), import(request), importWithRedirect(request), getFiles(), getColumnMappings() | 15 | 10 | 0% | 100%
Jour2 | ExistingApp | IMPORT TEST | VIEW | import/importtest – champ(fileInput1) | 3 | 2 | 0% | 100%
Jour2 | ExistingApp | GENERATEUR DATA | DATABASE | FUNCTION TRIGGER -> genererData → AllTable | 30 | 12 | 0% | 100%
Jour2 | ExistingApp | GENERATEUR DATA | METIER | DataGenerator - genererData() -> function SQL | 20 | 12 | 0% | 100%
Jour2 | ExistingApp | GENERATEUR DATA | CONTROLLER | DataGeneratorController - genererData() -> URL(/genererData) | 10 | 2 | 0% | 100%
Jour2 | ExistingApp | GITHUB | ENVIRONNEMENT | Branche,Repository | 10 | 5 | 0% | 100%
Jour2 | ExistingApp | EXCEPTION | METIER | InvoiceCalculator → getAmountDue() | 2 | 3 | 0% | 100%
Jour2 | ExistingApp | EXCEPTION | CONTROLLER | PaymentsController → addPayment() → condition (montant < montantDue*100 – 0.01) →flash_message_warning(Payment amount cannot exceed) | 2 | 3 | 0% | 100%
Jour2 | ExistingApp | CONNEXION | CONTROLLER | ApiAuthController → login() → logout() → refresh() | 30 | 2 | 0% | 100%
Jour2 | ExistingApp | CONNEXION | CONF | Config Token jwt | 18 | 4 | 0% | 100%
Jour2 | ExistingApp | CONNEXION | ROUTE | URL(auth/login) , ['middleware' => 'auth:api'] → URL(‘auth/logout’) | 2 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | ClientRest → getClientData() | 10 | 5 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/client’) | 5 | 1 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | Projet → getProjectData() | 12 | 0 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/project’) | 2 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | TaskRest → getTaskData() | 15 | 1 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/task’) | 2 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | OfferRest → getOfferData() | 8 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/offer’) | 2 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | InvoiceRest → getInvoiceData() , getMontantDue() | 10 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/invoice’),URL(‘api/montantdue’) | 12 | 6 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | PayementRest → getPaymentData() , updatePaymentAmount(),deletePayment() | 20 | 10 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | DATABASE | View chart1 : clients→ invoices → invoice_lines → payments | 18 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | DATABASE | View chart2 : payments→ invoices → invoice_lines | 17 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | DATABASE | View chart3 :invoices → invoice_lines → payments | 12 | 9 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | METIER | Chart1Model → getAllChart1() → chart1 | 10 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | METIER | Chart2Model → getAllChart2() → chart2 | 16 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | METIER | Chart3Model → getAllChart3() → chart3 | 17 | 3 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | Chart1Rest → chart1() | 4 | 3 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/chart1’) | 3 | 0 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | Chart2Rest → chart2() | 2 | 1 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/chart2’) | 1 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | REST | Chart3Rest → chart3() | 12 | 2 | 0% | 100%
Jour2 | ExistingApp | DASHBOARD | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/chart3’) | 2 | 2 | 0% | 100%
Jour2 | ExistingApp | CONFIGURATION | METIER | Setting → ADD COLUMN global_discount_rate | 3 | 1 | 0% | 100%
Jour2 | ExistingApp | CONFIGURATION | MIGRATION | Setting → ADD COLUMN global_discount_rate | 3 | 3 | 0% | 100%
Jour2 | ExistingApp | CONFIGURATION | REST | TauxRest → getTaux() ,UpdateTaux() | 20 | 2 | 0% | 100%
Jour2 | ExistingApp | CONFIGURATION | ROUTE | ['middleware' => 'auth:api'] → URL(‘api/taux’),['middleware' => 'auth:api'] → URL(‘api/update-taux’) | 12 | 2 | 0% | 100%
Jour2 | NewApp | AuthHeaders | Model | Fonction : createAuthHeaders() | 15 | 1 | 0% | 100%
Jour2 | NewApp | DETAILS | DTO | ClientDTO →ClientResponseDTO → ClientDetailResponseDTO → ClientModel | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | METIER | ClientModel : getAll() ,getDetails,totalClients | 25 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | CONTROLLER | ClientController : getClients(),getClientDetails(),URL(/api/spring/clients),URL(/api/spring/client/{externalId}), | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | AFFICHAGE | pages/client/clients → externalId : pages/client/show | 22 | 3 | 0% | 100%
Jour2 | NewApp | DETAILS | DTO | ProjectDTO →ProjecResponseDTO → ProjecDetailResponseDTO →ProjecModel | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | METIER | ProjecModel : getAll() ,getDetails,totalProjec | 25 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | CONTROLLER | ProjecController : getProjec(),getProjecDetails(),URL(/api/spring/projects),URL(/api/spring/project/{externalId}), | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | AFFICHAGE | pages/project/projects → externalId : pages/project/show | 22 | 3 | 0% | 100%
Jour2 | NewApp | DETAILS | DTO | TaskDTO →TaskResponseDTO → TaskDetailResponseDTO →TaskModel | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | METIER | TaskModel : getAll() ,getDetails,totalTask | 25 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | CONTROLLER | TaskController : getTask(),getTaskDetails(),URL(/api/spring/tasks),URL(/api/spring/task/{externalId}), | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | AFFICHAGE | pages/task/tasks → externalId : pages/task/show | 22 | 3 | 0% | 100%
Jour2 | NewApp | DETAILS | DTO | OfferDTO →OfferResponseDTO → OfferDetailResponseDTO →OfferModel | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | METIER | OfferModel : getAll() ,getDetails,totalOffer | 25 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | CONTROLLER | OfferController : getOffer(),getTaskDetails(),URL(/api/spring/offers),URL(/api/spring/offer/{externalId}), | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | AFFICHAGE | pages/offer/offers → externalId : pages/offer/show | 22 | 3 | 0% | 100%
Jour2 | NewApp | DETAILS | DTO | InvoiceDTO →InvoiceResponseDTO → InvoiceDetailResponseDTO →InvoiceModel | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | METIER | InvoiceModel : getAll() ,getDetails,totalInvoice | 25 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | CONTROLLER | InvoiceController : getInvoice(),getInvoiceDetails(),URL(/api/spring/invoices),URL(/api/spring/invoice/{externalId}), | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | AFFICHAGE | pages/invoice/invoices → externalId : pages/invoice/show | 22 | 3 | 0% | 100%
Jour2 | NewApp | DETAILS | DTO | PayementDTO →PayementResponseDTO → PayementDetailResponseDTO →PayementModel | 20 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | METIER | PayementModel : getAll() ,getDetails,totalPayment,update-montant(),delete-montant() | 32 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | CONTROLLER | PayementController : getPayement(),getPayementDetails(),showFormUpdate(),deletePayment,validUpdate(),,URL(/api/spring/payments),URL(/api/spring/payment/{externalId}),URL(/api/spring/update-montant/{externalId}),,URL(/api/spring/delete/{externalId}), | 25 | 2 | 0% | 100%
Jour2 | NewApp | DETAILS | AFFICHAGE | pages/payment/payments → externalId : pages/payment/show ,delete payment, formulaire-update-montant - | 34 | 3 | 0% | 100%
Jour2 | NewApp | DASHBOARD | DTO | Chart1DTO →Chart1ResponseDTO → Chart1DetailResponseDTO →Chart1Model | 20 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | METIER | Chart1Model : getAll() ,getDetails,totalChart1 | 25 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | CONTROLLER | Chart1Controller : getChart1()URL(/api/graph/chart1) | 20 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | DTO | Chart2DTO →Chart2ResponseDTO → Chart2DetailResponseDTO →Chart2Model | 20 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | METIER | Chart2Model : getAll() ,getDetails,totalChart2 | 25 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | CONTROLLER | Chart2Controller : getChart2(mois,annee)URL(/api/graph/chart2) | 20 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | DTO | Chart3DTO →Chart3ResponseDTO → Chart3DetailResponseDTO →Chart3Model | 20 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | METIER | Chart3Model : getAll() ,getDetails,totalChart3 | 25 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | CONTROLLER | Chart3Controller : getChart3(status)URL(/api/graph/chart3) | 20 | 2 | 0% | 100%
Jour2 | NewApp | DASHBOARD | CONTROLLER | Dashboard () → :totalClients , totalProjects,totalTasks,totalOffers,totalInvoices,totalPayments,(chart1Data,chart1Status),(chart2Status,chart2DataJson :years,selectedYear,selectedMonth),(chart3DataJson,statuses),URL(api/dashboard) | 30 | 20 | 0% | 100%
Jour2 | NewApp | DASHBOARD | AFFICHAGE | chart1 | 12 | 10 | 0% | 100%
Jour2 | NewApp | DASHBOARD | AFFICHAGE | chart2 | 12 | 10 | 0% | 100%
Jour2 | NewApp | DASHBOARD | AFFICHAGE | chart3 | 12 | 10 | 0% | 100%
Jour2 | NewApp | DASHBOARD | AFFICHAGE | TABLEAU DE BORD:total(client, projet, task,offer, invoice, payment) | 24 | 20 | 0% | 100%
Jour2 | NewApp | DASHBOARD | AFFICHAGE | Dashboard : include(chart1,chart2,chart3,tableaubord) | 24 | 20 | 0% | 100%
Jour2 | NewApp | CONFIGURATION | DTO | TauxDTO →TauxResponseDTO → TauxDetailResponseDTO →TauxModel | 20 | 2 | 0% | 100%
Jour2 | NewApp | CONFIGURATION | METIER | TauxModel : getTaux() ,getUpdateTaux | 25 | 2 | 0% | 100%
Jour2 | NewApp | CONFIGURATION | CONTROLLER | TauxController : getTaux(),getUpdateTaux(),URL(/api/spring/taux),URL(/api/spring/update-taux/{externalId}), | 20 | 2 | 0% | 100%
Jour2 | NewApp | CONFIGURATION | AFFICHAGE | Form : pages/conf/taux → champ(taux) | 22 | 3 | 0% | 100%